## stories
Title | Task | Complete | Task | Complete | Task | Complete | Task | Complete | Task | Complete | Task | Complete
As a user, I need to be able to identify the company | Add a header | x | Find an appropriate logo | x | Add the logo | x
As a user, I need to be able to list all the books | Set up a local express server | x | Store some sample books data | x | Retrieve the books data from the express server | x | Create a view for the books data | x | Deliver the data to the view | x | Deliver the view with the data to the user | x
As an admin, I need to be able to add a book | Create a view for adding books | x | Validate user input in the view | x | Link to the add book view from the books list | x | Create an express route for adding books | x | Validate user input in the route | No
As an admin, I need to be able to delete an existing book | Create a view for deleting books | N/A | Create a link to the delete view from the books list | x | Create a route for deleting books | x
As an admin, I need to be able to edit existing books | Create a view for editing books | x | Validate user input | x | Link to the edit view from the books list | x | Create a route for editing books | x | Validate user input on the route | No
As a user, I need to be able to link to a specific book | Create a view for reading a single book | x | Create a route for reading a single book | x
As a user, I need to be able to list all the authors | Update the data model to include authors | x | Add some seed author data | x | Create an authors list view | x | Create an authors list route | x
As a user, I need to be able to easily navigate between books and authors | Add an index page that links to the books list and authors list pages | x | Add a side navigation that's visible from the books list and authors list pages | x
As an admin, I need to be able to add an author | Create an add author view | x | Validate user input in the view | x | Create an add author route | x | Validate user input in the route | No
As an admin I need to be able to delete an existing author | Create delete author view | N/A | Create delete author route | x
As an admin, I need to be able to edit existing authors | Create an edit author view | x | Validate user input on the view | x | Create an edit author route | x | Validate user input on the route | No
As a user, I need to be able to link to a specific author | Create a view for a single author | x | Create a route for a single author | x
As a user, I need to be able to link to an author from a book. | Add links to single author views from the books list | No | Add links to single author views from individual books | No | Add links to single author views from delete books views | N/A
As a user, I need to be able to link to a book from an author | Add links to single book views from authors list | x | Add links to single book views from single author view | x | Add links to single book views from delete author view | N/A
As a user, I need to be able to filter books by genre | Add a drop down for genres to the books list | x | When a value is selected from the list, only show books from that genre | x
As a user, I need to limit the number of book results I receive at a time | Limit the display on the books list page to 10 books per page | x | Link another page if there are more than 10 | x | Link to a previous page if there are fewer than 10 | x
As a user, I need to limit the number of authors I receive at a time | Limit the display on the authors page to 10 authors per page | x | Link to another page if there are more than 10 authors | x | Link to a previous page if there are fewer than 10 authors | x
As a user, I need to search for books | Add a field to the books list page to enter a search term for a book | x | Add the ability to search for a record to the books list route | N/A
As a user, I need to be able to search for authors | Add a field to the authors list page to enter a search term for an author | x | Add the ability to search for a record to the authors route | N/A
As a user, I need to be able to search for books and authors | Add the ability to enter a search term on the index page for authors or books | x | Add a route that can do a general search between books and authors | x | Add a view that displays the results of the search | x
As a user, I need to be able see the total number of books | On the books list page, display the total number of books in the database | x
As a user, I need to be able to see the total number of authors | On the authors list page, display the total number of authors in the database | x